## Sheet1
Legend: | Sprint deadline indictaed in brackets
Pair number indicated in highlighted boxes
Project Part | Module | Sprint 0 (02/22) | Sprint 1 (03/01) | Sprint 2 (03/08) | Sprint 3 (03/15) | Sprint 4 (03/22) | Sprint 5 (03/29) | Sprint 6 (04/05)
Part 4
| XML | All
| Task Basic |  | 1 | 1
| Task Details |  | 2
| User Profile |  | 3
| Searching |  |  | 2
| ElasticSearch |  |  | 3
| Task Bidding |  |  |  | All
Part 5
| Task Assignment |  |  |  |  | 1
| Task Done | [5 empty] | 1
| Offline Behaviour |  |  |  |  | 2
| Photographs |  |  |  |  | 3
| Geolocation | [5 empty] | 2
| Wow Factor | [5 empty] | 3 | All